## readme
This file logs rapid response actions performed under work package C2, which intends to eradicate new populations of emerging plants and crayfish species and alert list species.
The file has been initiated and maintained by ANB (Michiel Stas, Niels Schild).
The data has been curated by INBO (Bram D'hondt) since 2026-02.
The data is structured in a way that allows easy digest by software for data publication and analysis.
When making changes, please try to adhere to current vocabulary as much as possible.
Do not merge cells.
In case of questions, please contact niels.schild@vlaanderen.be + bram.dhondt@inbo.be.
Tabs
C2_populations | : | C2 populations under management
C2_visits_plants | : | overview of actions within the populations from the previous tab
C2_pops_not-managed | : | C2 populations not under management (yet)

## C2_populations
RIPARIAS | population code |  | target species |  | site details | [5 empty] | partners |  | site details |  | INITIAL population details |  |  |  |  | END-OF-PROJECT population details |  |  | eradication status
Action | popcode | pc_old | group | species | latitude | longitude | site | municipality | region | RSU | organisation | ownership | habitat | waterbody_size_m² | INITIAL_m² | INITIAL_other_quantity | INITIAL_other_unit | comments | eradication_feasibility | assessment_date | REMAINING_size | REMAINING_size_unit | assessment_date | visit_base | eradication_status
C2 | Zl1 | P11 | plants | Zizania latifolia | 50°48'44,6"N | 4°16'19,5"E | Vogelzang/Erasmus | Anderlecht | BRU | 42 | BE, ETH | BE | Pond | 2574 | 843 |  |  | Highly invaded pond with natural bank. Stones and geo-textile in the bank provide challenges for plant removal. | 3_maybe | 2025-12-15 | 457 | m2 | 2026-08-26 | 3 | not
C2 | Zl2 |  | plants | Zizania latifolia | 50°47'28,9"N | 4°24'52,9"E | Silex | Watermaal-Bosvoorde | BRU | 44 | BE, ETH | BE/ LRBPO | Pond | 10127 | 196.5 |  |  |  | 4_yes | 2026-07-30 | 0 | m2 | 2026-08-26 | 3 | ERADICATED
C2 | Zl3 |  | plants | Zizania latifolia | 50°48'51,5"N | 4°26'30,4"E | Rouge cloitre | Auderghem | BRU | 44 | BE, ETH | BE | Pond | 9620 | 150 |  |  |  | 4_yes | 2026-07-30 | 0 | m2 | 2026-08-04 | 2 | ERADICATED
C2 | Zl6 |  | plants | Zizania latifolia | 50°49'21,9"N | 4°39'13,3"E | Zoet water | Oud-Heverlee | FLA | 13 | ANB | municipality | Pondbank | 13600 | 1300 | 390 | ton |  | 3_maybe | 2026-08-14 | 930 | m2 | 2026-08-17 | 2 | not
C2 | Zl7 |  | plants | Zizania latifolia | 50°42'58,0"N | 4°25'54,5"E | Argenteuil - de Séjournet | Waterloo | WAL | 9 | CR Senne/Dyle-Gette | private | Pond | 6000 | 270 |  | m3 | Opportunistic management using the mower (by amphibious boatused for the management of the Hydrocotyle ranunculoides) | 3_maybe | 2026-05-13 | 0 | m3 | 2026-08-04 | 2 | ERADICATED
C2 | Zl8 |  | plants | Zizania latifolia | 50°47'25,0"N | 4°24'48,7"E | ISB (International School of Brussels) | Watermaal-Bosvoorde | BRU | 44 | BE | Private : ISB | Pond | 30 | 50 | 40 | plants |  | 3_maybe | 2026-07-30 | 20 | plants | 2026-08-26 | 2 | not
C2 | Zl9 |  | plants | Zizania latifolia | 50°50'35,2"N | 4°26'21,6"E | Struybeek | Woluwe-Saint-Lambert | BRU | . | BE, ETH | BE | Swamp | 5200 | 150 |  |  |  | 4_yes | 2026-07-30 | 0 | m2 | 2026-08-26 | 2 | ERADICATED
C2 | La1 | P09 | plants | Lysichiton americanus | 50°48'33,9"N | 4°25'43,6"E | Parc Sény | Auderghem | BRU | 44 | BE | BE | Riverbank | N/A |  | 2 | plants |  | 4_yes | n/a | n/a | n/a | 2026-08-04 | 3 | ERADICATED
C2 | La2 |  | plants | Lysichiton americanus | 50°51'18,9"N | 4°21'48,3"E | Parc Botanique | Saint-Josse-ten-Noode | BRU | 46 | BE, Jardiniers Botaniques | BE | Fountain | N/A |  | 15 | plants |  | 4_yes | 2025-11-01 | 0 | plants | 2026-08-26 | 2 | ERADICATED
C2 | La3 | P01 | plants | Lysichiton americanus | 50°43'46,5"N | 4°44'22,8"E | Grosses Pierres (Rue Fond du Village) | Grez-Doiceau | WAL | 8 | CR Senne/Dyle-Gette | Public | River bank | N/A |  | 1 | plants |  | 4_yes | 2026-06-04 | 0 | plants | 2026-08-04 | 3 | ERADICATED
C2 | La4 | P02 | plants | Lysichiton americanus | 50°42'10,9"N | 4°30'4,76"E | Renipont | Lasne | WAL | 6 | CR Senne/Dyle-Gette | Public | Pond | N/A |  | 6 | plants |  | 4_yes | 2026-03-20 | 0 | plants | 2026-08-04 | 3 | ERADICATED
C2 | La5 | P12 | plants | Lysichiton americanus | 50°41'57,0"N | 4°35'39,2"E | Aquaproduction | Wavre | WAL | 7 | CR Senne/Dyle-Gette | private | River bank and floodplain | N/A |  | 200 | plants |  | 4_yes | 2026-06-04 | 25 | plants | 2026-08-27 | 3 | not
C2 | La6 |  | plants | Lysichiton americanus | 50°43'12,1"N | 4°26'01,0"E | Argenteuil - Delwart | Waterloo | WAL | 9 | CR Senne/Dyle-Gette | private | River bank and floodplain | N/A |  | 29 | plants |  | 4_yes | 2026-05-13 | 0 | plants | 2026-08-04 | 3 | ERADICATED
C2 | La7 |  | plants | Lysichiton americanus | 50°35'41,1"N | 4°30'05,8"E | Marcel Rayez - Rue Fosty Genappe | Genappe | WAL | 2 | CR Senne/Dyle-Gette | private | River bank and floodplain | N/A |  | 70 | plants | Removal includes L. camchatscensis. | 4_yes | 2026-06-XX | 2 | plants | 2026-08-26 | 3 | not
C2 | La8 |  | plants | Lysichiton americanus | 50°38'51,0"N | 4°22'30,0"E | Badaud - Rue Comte de Meëus | Braine l'Alleud | WAL | 37 | CR Senne/Dyle-Gette | private | River bank and floodplain | N/A |  | 30 | plants |  | 4_yes | 2026-04-15 | 1 | plants | 2026-08-27 | 3 | not
C2 | La10 |  | plants | Lysichiton americanus | 50°38'22,6"N | 4°31'43,1"E | Rue du sablon | Genappe | WAL | 1 | CR Senne/Dyle-Gette | private | Floodplain | N/A |  | 3 | plants |  | 4_yes | 2026-05-21 | 0 | plants | 2026-08-04 | 3 | ERADICATED
C2 | La11 |  | plants | Lysichiton americanus | 50°37'45,5"N | 4°07'19,2"E | Hameau de la Favarge | Braine-le-Comte | WAL | 33 | CR Senne/Dyle-Gette | private | Pond | N/A |  | 5 | plants |  | 4_yes | 2026-05-22 | 0 | plants | 2026-08-27 | 3 | ERADICATED
C2 | La12 |  | plants | Lysichiton americanus | 50°40'07,7"N | 4°23'06,6"E | Municipality | Braine-l'Alleud | WAL | 37 | Riverine | municipality | Pond | N/A |  | 10 | plants |  | 4_yes | 2026-05-15 | 7 | plants | 2026-08-27 | 3 | not
C2 | La13 |  | plants | Lysichiton americanus | 50°41'53,3"N | 4°35'46,8"E | Aquatic design | Wavre | WAL | 7 | Jardiniers | private | Pond | N/A |  | 40 | plants |  | 4_yes | 2026-05-21 | 0 | plants | 2026-08-04 | 3 | ERADICATED
C2 | La14 |  | plants | Lysichiton americanus | 50°41'48,9"N | 4°39'54,4"E | Rue Tienne du Chenois | Chaumont-Gistoux | WAL | 7 | CR Senne/Dyle-Gette | private | Pond bank | N/A |  | 7 | plants |  | 4_yes | 2026-06-04 | 2 | plants | 2026-08-27 | 3 | not
C2 | La15 |  | plants | Lysichiton americanus | 50°37'42,7"N | 4°27'49,8"E | Chemin des Crolis | Glabais | WAL | 1 | CR Senne/Dyle-Gette | private | Pond | N/A |  | 30 | plants |  | 4_yes | 2026-06-XX | 0 | plants | 2026-08-26 | 2 | ERADICATED
C2 | La16 |  | plants | Lysichiton americanus | 50°36'44.2"N | 4°30'12.7"E | Rue du Château 1b | Genappe | WAL | 1 | CR Senne/Dyle-Gette | . | Floodplain | N/A |  | 40 | plants | Managed by riverine in 2026 after reception letter of DNF | 3_maybe | 2026-05-27 | 100 | plants | 2026-08-27 | 2 | not
C2 | La17 |  | plants | Lysichiton americanus | 50°34'47,3"N | 4°38'26,7"E | Rue Octave Lotin | Chastre | WAL | 2 | Riverine | private | Pond bank | N/A |  | 10 | plants |  | 4_yes | 2026-05-07 | 0 | plants | 2026-08-27 | 2 | ERADICATED
C2 | La18 |  | plants | Lysichiton americanus | 50°35'23,0"N | 4°38'25,3"E | Rue du Bief | Chastre | WAL | 2 | CR Senne/Dyle-Gette | private | Floodplain | N/A |  | 30 | plants |  | 4_yes | 2026-05-28 | 15 | plants | 2026-08-27 | 2 | not
C2 | La20 |  | plants | Lysichiton americanus | 50°41'40.4"N | 4°29'40.9"E | Rue de la Lasne 98-100 | Lasne | WAL | 6 | CR Senne/Dyle-Gette |  | Floodplain | N/A | 100 |  |  | Managed by riverine in 2026 after reception letter of DNF | 3_maybe | n/a | n/a | n/a | 2026-08-28 | 1 | n/a
C2 | La21 |  | plants | Lysichiton americanus | 50°44'02,2"N | 4°42'11,9"E | Château de Piétrebais | Grez-Doiceau | WAL | 8 | CR Senne/Dyle-Gette | private | Pond | N/A |  | 60 | plants |  | 4_yes | 2026-06-04 | 8 | plants | 2026-08-27 | 3 | not
C2 | La22 |  | plants | Lysichiton americanus | 50°43'46,6"N | 4°44'23,1"E | Fond du Moulin | Grez-Doiceau | WAL | 8 | CR Senne/Dyle-Gette | private | Floodplain | N/A |  | 1 | plants |  | 4_yes | 2026-06-04 | 0 | plants | 2026-08-04 | 3 | ERADICATED
C2 | La23 |  | plants | Lysichiton americanus | 50°43'46,6"N | 4°45'42,7"E | Rue Fond du Village 35 | Grez-Doiceau | WAL | 8 | CR Senne/Dyle-Gette | private | River bank and floodplain | N/A |  | 100 | plants |  | 3_maybe | n/a | n/a | n/a | 2026-08-28 | 1 | n/a
C2 | La24 |  | plants | Lysichiton americanus | 50°43'40,9"N | 4°17'13,1"E | Jacquemart | Braine-le-Château | WAL | 36 | CR Senne/Dyle-Gette | private | River bank and floodplain | N/A |  | 50 | plants |  | 3_maybe | 2026-04-16 | 36 | plants | 2026-08-27 | 2 | not
C2 | La25 |  | plants | Lysichiton americanus | 50°42'53,8"N | 4°42'24,6"E | Chemin du Grand Sart | Chaumont-Gistoux | WAL | 8 | Riverine | private | Pond bank | N/A |  | 2 | plants | The riverine cuts the flower every year. | 4_yes | 2026-06-04 | 0 | plants | 2026-08-04 | 2 | ERADICATED
C2 | La27 |  | plants | Lysichiton americanus | 50°41'16.3"N | 4°15'25.1"E | Rue Mathias 11 | Braine-le-Château | WAL | 36 | CR Senne/Dyle-Gette | private | Floodplain | N/A |  | 5 | plants | The riverine wanted to keep the mother plant | 2_probably not | n/a | n/a | n/a | 2026-08-28 | 1 | n/a
C2 | La28 |  | plants | Lysichiton americanus | 50°43'38,0"N | 4°33'16,7"E | chemin du Plagniau | Rixensart | WAL | 12 | CR Senne/Dyle-Gette | private | Pond and riverbank | 60 |  | 8 | plants | The riverine plan to manage the plants following our recommendations | 4_yes | n/a | n/a | n/a | 2026-08-28 | 1 | n/a
C2 | Pco1 |  | plants | Pontederia cordata | 50°51'18,9"N | 4°21'48,4"E | Parc Botanique | Saint-Josse-ten-Noode | BRU | 46 | BE, Jardiniers Botaniques | BE | Fountain | 6 | 3 |  |  |  | 4_yes | 2025-12-15 | 0 | m2 | 2026-08-26 | 2 | ERADICATED
C2 | Pco2 |  | plants | Pontederia cordata | 50°53'07,0"N | 4°20'55,1"E | Jardins du Fleuriste | Ville de Bruxelles | BRU | 47 | BE, Jardiniers Fleuristes | BE | Pond | 921.75 | 14.7 |  |  |  | 4_yes | 2026-07-31 | 7 | m2 | 2026-08-26 | 2 | not
C2 | Lp1 | P08 | plants | Ludwigia peploides | 50°40'41,4"N | 4°32'26,3"E | Ottignies-LLN - Rue de Pinchart | Ottignies-LLN | WAL | 7 | CR Senne/Dyle-Gette | private | Pond | 550 | 22 |  |  |  | 3_maybe | 2026-08-04 | 7 | plants | 2026-08-26 | 6 | not
C2 | Lp2 | P10 | plants | Ludwigia peploides | 50°37'02,5"N | 4°30'59,3"E | Rue du chateau 39 | Genappe | WAL | 1 | CR Senne/Dyle-Gette | private | Pond |  |  | 10 | plants |  | 4_yes | n/a | n/a | n/a | 2026-08-04 | 3 | ERADICATED
C2 | Lp3 |  | plants | Ludwigia peploides | 50°37'05,4"N | 4°31'07,7"E | Rue du chateau 65 | Genappe | WAL | 1 | CR Senne/Dyle-Gette | private | Pond |  |  | 0.5 | m3 |  | 3_maybe | 2026-05-27 | 0.02 | m3 | 2026-08-27 | 2 | not
C2 | Lp4 |  | plants | Ludwigia peploides | 50°38'20,0"N | 4°30'44,6"E | Rue de Wanroux | Genappe | WAL | 1 | CR Senne/Dyle-Gette |  | Beaver floodplain |  | 2 | 25 | L |  | 4_yes | 2026-08-XX | 0 | m2 | 2026-08-27 | 2 | ERADICATED
C2 | Ch1 | P03 | plants | Crassula helmsii | 50°38'59,9"N | 4°33'48,1"E | Parc de Wisterzée | Court-St-Etienne | WAL | 7 | Brabant Wallon | Province BW | Pond | 1100 | 200 |  |  |  | 2_probably not |  |  |  | 2026-08-04 | 2 | not
C2 | Ch2 | P04 | plants | Crassula helmsii | 50°45'14,7"N | 4°39'41,9"E | Archennes | Grez-Doiceau | WAL | 8 | Riverine | private | Pond | 15 | 10 |  |  |  | 1_no |  |  |  | 2026-08-04 | 5 | not
C2 | Ch3 | P06 | plants | Crassula helmsii | 50°40'32,0"N | 4°35'38,4"E | Bois de Lauzelle (Mare UCL) | Ottignies | WAL | 7 | UCL | private | Pond | 200 | 200 |  |  | Pond almost totally covered (200m²). | 1_no | 2026-06-04 | 0.005 | m3 | 2026-08-04 | 3 | not
C2 | Ch4 | P07 | plants | Crassula helmsii | 50°44'11,6"N | 4°42'29,0"E | Chaussée de Jodoigne | Grez-Doiceau | WAL | 8 | Riverine | private | Pond | 40 | 20 |  |  |  | 4_yes | n/a | n/a | n/a | 2026-08-28 | 2 | ERADICATED
C2 | Ch5 |  | plants | Crassula helmsii | 50°41'45,2"N | 4°13'15,8"E | Erpetolia | Tubize | WAL | 35 | CR Senne/Dyle-Gette | private | Pond | 30 | 3 |  |  |  | 3_maybe | 2026-05-XX | 3 | m2 | 2026-08-27 | 4 | not
C2 | Ch6 |  | plants | Crassula helmsii | 50°41'40,3"N | 4°15'32,7"E | Bruyère Mathias | Braine-le-Château | WAL | 36 | CR Senne/Dyle-Gette | private | Pond | 105 | 40 | 1.6 | m3 | Mixed with Hydrocotyle ranunculoides. | 3_maybe | 2026-06-XX | 0.01 | m3 | 2026-08-26 | 3 | not
C2 | Ch7 |  | plants | Crassula helmsii | 50°33'48,4"N | 4°06'29,7"E | TommorowLab | Soignies | WAL | 25 | CR Senne/Dyle-Gette | Community garden | Pond |  |  | 0.2 | m3 |  | 3_maybe | 2026-06-XX | 0.002 | m3 | 2026-08-26 | 3 | not
C2 | Lm1 |  | plants | Lagarosiphon major | 50°41'45,2"N | 4°13'15,8"E | Erpetolia | Tubize | WAL | 35 | CR Senne/Dyle-Gette | private | Pond | 1 | 1 |  |  |  | 4_yes | 2026-05-15 | 0 | m2 | 2026-08-04 | 3 | ERADICATED
C2 | Ed1 | P05 | plants | Egeria densa | 50°53'05,0"N | 4°18'06,7"E | Laarbeekbos | Jette | BRU | 47 | BE | BE | Pond | 41.4 | 1 | 10 | plants | Small, isolated pond. Emerging population. | 4_yes | n/a | n/a | n/a | 2026-08-04 | 2 | ERADICATED
C2 | Ed2 |  | plants | Egeria densa | 50°39'53,1"N | 4°06'51,8"E | Voie des Courts | Rebecq | WAL | 33 | CR Senne/Dyle-Gette | private | Pond | 140 | 80 |  |  |  | 3_maybe | 2026-05-22 | 0 | m2 | 2026-08-04 | 4 | ERADICATED
C2 | Ed3 |  | plants | Egeria densa | 50°40'18,2"N | 4°22'34,4"E | Parc de l'Alliance | Braine-l'Alleud | WAL | 37 | CR Senne/Dyle-Gette | municipality | Pond | 2890 | 2890 | 40.163 | m3 |  | 3_maybe | 2026-05-15 | 0 | m2 | 2026-08-04 | 2 | ERADICATED
C2 | Ed4 |  | plants | Egeria densa | 50°33'48,4"N | 4°06'29,7"E | TommorowLab | Soignies | WAL | 25 | CR Senne/Dyle-Gette | Community garden | Pond |  |  | 0.03 | m3 |  | 3_maybe | 2026-XX-XX | 1 | m3 | 2026-08-27 | 2 | not
C2 | Eg1 |  | plants | Erythranthe guttata | 50°47'55,2"N | 4°17'03,6"E | Zuunbeek Wildersportcomplex | Sint-Pieters-Leeuw | FLA | 38 | VMM |  | River bank and floodplain | N/A | 10 |  |  |  | 4_yes | 2026-07-09 | 0 | m2 | 2026-08-04 | 4 | ERADICATED
C2 | Eg2 |  | plants | Erythranthe guttata | 50°42'49,8"N | 4°13'48,1"E | Overstort Zenne-Kanaal Lembeek | Halle | FLA | 39 | VMM/Vlaamse Waterweg | - non-partner public body | Floodplain | N/A | 200 |  |  |  | 3_maybe | 2026-07-09 | 3420 | m2 | 2026-08-04 | 4 | not
C2 | Eg3 |  | plants | Erythranthe guttata | 50°58'36,4"N | 4°29'04,2"E | Weerdse visvijver | Zemst | FLA | 50 | ANB | ANB | Pond bank | N/A |  |  |  |  | 4_yes | 2026-07-09 | 1.5 | m2 | 2026-08-04 | 3 | not
C2 | Eg4 |  | plants | Erythranthe guttata | 50°43'34,5"N | 4°41'58,0"E | Basse-Biez | Grez-Doiceau | WAL | 8 | CR Senne/Dyle-Gette | private | Floodplain | N/A | <1 | 2 | plants | Not a pond. | 4_yes | n/a | n/a | n/a | 2026-08-04 | 2 | ERADICATED
C2 | Eg5 |  | plants | Erythranthe guttata | 50°40'13,6"N | 4°16'08,4"E | Sentier Muraes | Braine-le-Château | WAL | 36 | CR Senne/Dyle-Gette | municipality | Floodplain | N/A | <1 | 3 | plants |  | 4_yes | 2026-05-28 | 9 | plants | 2026-08-27 | 3 | not
C2 | Pj1 |  | plants | Petasites japonicus | 50°51'17,5"N | 4°29'25,0"E | Wezembeek | Wezembeek-Oppem | FLA | 48 | VMM, gemeente Wezembeek-Oppem | - RIPARIAS partner, non-partner public body | River bank and floodplain |  | 85 |  |  |  | . | 2026-04-14 | 71 | plants | 2026-08-04 | 3 | not
C2 | Pj2 |  | plants | Petasites japonicus | 50°37'48,6"N | 4°28'09,9"E | Cala | Genappe | WAL | 1 | CR Senne/Dyle-Gette | private | River bank and floodplain | N/A | 80 |  |  |  | 4_yes | 2026-XX-XX | 0 | plants | 2026-08-27 | 3 | ERADICATED
C2 | Kp1 |  | plants | Koenigia polystachya | 50°48'17,0"N | 4°23'26,5"E | Simonaustraat | Elsene | BRU | 44 | BE |  | Park | / | 250 | 250 |  |  | 3_maybe | 2026-07-30 | 30 | m2 | 2026-08-26 | 3 | not
C2 | Kp2 |  | plants | Koenigia polystachya | 50°51'45,0"N | 4°41'05,5"E | Kasteelpark Arenberg | Leuven | FLA | 15 | ANB, KULeuven | KULeuven | pondbank | N/A | 1.25 |  |  |  | . | 2026-06-23 | 38 | plants | 2026-08-28 | 2 | not
C2 | Pcl1 | C01 | crayfish | Procambarus clarkii | 50°42'59,7"N | 4°43'03,5"E | Biez | Grez-Doiceau | WAL | 8 | CR Senne/Dyle-Gette & SPW | private | Pond | 1500 |  |  |  |  | 3_maybe |  |  |  | 2026-08-04 | . | .
C2 | Pcl2 | C02 | crayfish | Procambarus clarkii | 50°48'24,2"N | 4°25'40,9"E | Tenreukenvijver | Watermaal-Bosvoorde | BRU | 44 | BE | BE | Pond | N/A |  |  |  | Pond drawdown is difficult (shallow pond fed by river). | 2_probably not |  |  |  | 2026-08-04 | . | .

## C2_visits_plants
population reference | visit | [7 empty] | removal | [5 empty] | suggested follow-up action
popcode | visit_organiser | nr | year | month(s)/season | plant_presence | visit_intent | visit_executor | visit_nr_persons | technique | technique_sub | quantity | unit | completeness | comments | follow_up | photos
Zl1 | BE | 1 | 2023 | Oct-Nov | yes | plant removal | contractant | 5 people + truck drivers | mechanical | excavator(s) | 15 | truck containers |  |  | follow next year(s) | yes (Xavier)
Zl1 | BE | 2 | 2024 | . | yes | plant removal | contractant | . | . | . | . | . | . | . | . | .
Zl1 | BE | 3 | 2025 | Dec | yes | kpi_check | BE | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Zl2 | BE | 1 | 2024 | Oct | yes | plant removal |  | 3 people | mechanical |  | 200 | m² | all plants |  | follow next year(s) | yes (Arnaud)
Zl2 | BE | 2 | 2025 | summer | yes | plant removal |  | 1 people | manual | hand-pulling | 1 | plant | all plants |  | follow next year(s) | yes (Arnaud)
Zl2 | BE | 3 | 2026 | Jul | no | kpi_check | BE | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Zl3 | BE | 1 | 2024 | Nov | yes | plant removal |  | 4 people | mechanical |  | 150 | m² | all plants |  | follow next year(s) | yes (Arnaud)
Zl3 | BE | 2 | 2025 | summer | no | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a |  | follow next year(s) | yes (Arnaud)
Zl6 | ANB | 1 | 2025 | Sep | yes | site treatment | contractant | . | mechanical |  | 675 | m² |  | plant removal before desilting the pond; 389,76 tonnes | follow next year(s)
Zl6 | INBO | 2 | 2026 | Aug | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | . | .
Zl7 | CR Senne/Dyle-Gette | 1 | 2025 | Sep-Oct | yes | site treatment | contractant | . | mechanical |  |  |  |  | Management before manual removal; mowing by amphibious boat. | follow next year(s) | yes
Zl7 | . | 2 | 2026 | May | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
Zl8 | BE | 1 | 2025 | Oct | yes | plant removal | BE | 4 people | manual |  | 15 | m² | all plants |  | follow next year(s) | yes (Arnaud)
Zl8 | BE | 2 | 2026 | Jul | yes | kpi_check | BE | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Zl9 | BE | 1 | 2026 | Jan | yes | site treatment | BE | . | manual | tarping | 150 | m² | all plants | covered with opaque tarpaulin | follow next year(s)
Zl9 | BE | 2 | 2026 | Jul | no | kpi_check | BE | . | n/a | n/a | n/a | n/a | n/a | . | . | .
La1 | BE | 1 | 2023 | Jul | yes | plant removal | BE | 4 people | manual |  | 4 | plants | all plants |  | follow next year(s) | yes (Xavier)
La1 | BE | 2 | 2024 | May | yes | plant removal |  | 1 people | manual |  | 2 | plants | all plants |  | follow next year(s) | yes
La1 | BE | 3 | 2025 | summer | no | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a |  | follow next year(s)
La2 | BE | 1 | 2024 | Sep | yes | plant removal |  | 2 people | manual |  | 5 | m² | all plants |  | follow next year(s) | yes
La2 | BE | 2 | 2025 | Nov | no | kpi_check | BE | . | n/a | n/a | n/a | n/a | n/a | . | . | .
La3 | CRDG | 1 | 2021 | Apr | yes | plant removal | CRDG | 1 people | manual | digging | 7 | plants | all plants |  | follow next year(s)
La3 | CRDG | 2 | 2022 | . | no | n/a |  | 1 people | n/a | n/a
La3 | CRDG | 3 | 2026 | Jun | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
La4 | CRDG | 1 | 2021 | May | yes | plant removal |  | 3 people | manual | digging | 6 | plants | all plants |  | follow next year(s)
La4 | CRDG | 2 | 2022 | . | no |  |  | 1 people | n/a | n/a | n/a | n/a
La4 | CRDG | 3 | 2026 | March | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
La5 | CR Senne/Dyle-Gette | 1 | 2024 | May | yes | plant removal |  | 5 people | manual | digging | 150 | plants | all plants |  | follow next year(s)
La5 | CR Senne/Dyle-Gette | 2 | 2025 | Jul | yes | plant removal |  | 1 people | manual | digging | 18 | plants | all plants |  | follow next year(s)
La5 | CR Senne/Dyle-Gette | 3 | 2026 | Jun | yes | kpi_check |  |  | n/a | n/a | 25 | plants |  |  | follow next year(s) | no
La5 | CR Senne/Dyle-Gette | 4 | 2026 | Jun | yes | plant removal | . | 4 people | manual | digging | 41 | plants | all plants | . | follow next year(s) | no
La6 | CR Senne/Dyle-Gette | 1 | 2024 | summer | yes | plant removal |  | 4 people | manual | digging | 29 | plants | all plants |  | follow next year(s) | yes
La6 | CR Senne/Dyle-Gette | 2 | 2025 | Jul | no | n/a |  | 2 people | n/a | n/a | n/a | n/a |  |  | follow next year(s) | no
La6 | CR Senne/Dyle-Gette | 3 | 2026 | May | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
La7 | CR Senne/Dyle-Gette | 1 | 2024 | summer | yes | plant removal |  | 5 people | manual | digging | 70 | plants | all plants |  | follow next year(s)
La7 | CR Senne/Dyle-Gette | 2 | 2025 | May | yes | plant removal |  | 3 people | manual | digging | 3 | plants | all plants |  | follow next year(s) | no
La7 | CR Senne/Dyle-Gette | 3 | 2026 | Jun | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | 2 plants | follow next year(s) | no
La7 | CR Senne/Dyle-Gette | 4 | 2026 | Jun | yes | plant removal |  | 1 people | manual | digging | 2 | plants | all plants |  | follow next year(s) | no
La8 | CR Senne/Dyle-Gette | 1 | 2024 | summer | yes | plant removal |  | 3 people | manual | digging | 30 | plants | all plants |  | follow next year(s) | no
La8 | CR Senne/Dyle-Gette | 2 | 2025 | summer | yes | plant removal |  | 2 people | manual | digging | 7 | plants | all plants |  | follow next year(s)
La8 | CR Senne/Dyle-Gette | 3 | 2026 | Apr | yes | kpi_check | . | ? | n/a | n/a | 1 | plant | . | . | follow next year(s) | no
La8 | CR Senne/Dyle-Gette | 4 | 2026 | Apr | yes | plant removal | . |  | manual | digging | 1 | plant | . | . | follow next year(s) | no
La10 | CR Senne/Dyle-Gette | 1 | 2024 | summer | yes | plant removal |  | 2 people | manual | digging | 3 | plants | all plants |  | follow next year(s)
La10 | CR Senne/Dyle-Gette | 2 | 2025 | Jun | no | n/a |  | 1 people | n/a | n/a | n/a | n/a |  |  | follow next year(s)
La10 | CR Senne/Dyle-Gette | 3 | 2026 | May | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
La11 | CR Senne/Dyle-Gette | 1 | 2024 | Oct | yes | plant removal |  | 1 people | manual | digging | 5 | plants | all plants |  | follow next year(s) | yes
La11 | CR Senne/Dyle-Gette | 2 | 2025 | Oct | no | n/a |  | 2 people | n/a | n/a | n/a | n/a |  |  | none
La11 | CR Senne/Dyle-Gette | 3 | 2026 | May | no | kpi_check | . | . | n/a | n/a | n/a | n/a |  |  | none | no
La12 | Riverine | 1 | 2024 | summer | yes | plant removal |  | . | manual | digging | 10 | plants | all plants |  | follow next year(s)
La12 | CR Senne/Dyle-Gette | 2 | 2025 | summer | yes | plant removal |  | 2 people | manual | digging | 12 | plants | all plants |  | follow next year(s) | yes
La12 | CR Senne/Dyle-Gette | 3 | 2026 | May | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
La12 | CR Senne/Dyle-Gette | 4 | 2026 | May | yes | plant removal | . | 1 people | manual | digging | 7 | plants | all plants | . | follow next year(s) | .
La13 | Jardiniers Aquatic Design | 1 | 2024 | spring | yes | plant removal |  | . | manual | digging | 40 | plants | all plants |  | follow next year(s)
La13 | Jardiniers Aquatic Design | 2 | 2025 | May | no | n/a |  | 1 people | n/a | n/a | n/a | n/a |  |  | follow next year(s)
La13 | Jardiniers Aquatic Design | 3 | 2026 | May | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
La14 | CR Senne/Dyle-Gette | 1 | 2024 | summer | yes | plant removal |  | 1 people | manual | digging | 7 | plants | all plants |  | follow next year(s)
La14 | CR Senne/Dyle-Gette | 2 | 2025 | Jul | yes | plant removal |  | 2 people | manual | digging | 26 | plants | all plants |  | follow next year(s)
La14 | CR Senne/Dyle-Gette | 3 | 2026 | Jun | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
La14 | CR Senne/Dyle-Gette | 4 | 2026 | Jun | yes | plant removal | . | 2 people | manual | digging | 2 | plants | all plants | . | follow next year(s) | .
La15 | CR Senne/Dyle-Gette | 1 | 2025 | Apr | yes | plant removal |  | 1 people | manual | digging | 30 | plants | all plants | Managed by riverine in 2025 after reception letter of DNF | follow next year(s) | no
La15 | CR Senne/Dyle-Gette | 2 | 2026 | Jun | no | kpi_check | . | n/a | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | no
La16 | Riverine | 1 | 2025 | - | yes | plant removal |  | 1 people | manual | digging | 50 | plants | visible plants |  | follow next year(s) | .
La16 | CR Senne/Dyle-Gette | 2 | 2026 | May | yes | kpi_check | . | n/a | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | no
La16 | CR Senne/Dyle-Gette | 3 | 2026 | May | yes | plant removal |  | 2 people | manual | digging | 100 | plants | all plants |  | follow next year(s) | no
La17 | Riverine | 1 | 2025 | Jun | yes | plant removal |  | . | manual | digging | 10 | plants | all plants |  | follow next year(s) | no
La17 | CR Senne/Dyle-Gette | 2 | 2026 | May | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
La18 | CR Senne/Dyle-Gette | 1 | 2025 | May | yes | plant removal |  | 3 people | manual | digging | 25 | plants | all plants |  | follow next year(s) | no
La18 | CR Senne/Dyle-Gette | 2 | 2026 | May | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
La18 | CR Senne/Dyle-Gette | 3 | 2026 | May | yes | plant removal | . | 1 people | manual | digging | 15 | plants | all plants | . | follow next year(s) | .
La20 | CR Senne/Dyle-Gette | 1 | 2026 | June | yes | plant removal | . | 2 people | manual | digging | 400 | plants | all plants | . | follow next year(s) | .
La21 | Riverine | 1 | 2025 | Apr | yes | plant removal |  | 1 people | manual |  | 1 | plants |  | 1 big plant | follow next year(s) | no
La21 | CR Senne/Dyle-Gette | 2 | 2025 | May | yes | plant removal |  | 1 people | manual | digging | 60 | plants | all plants |  | follow next year(s)
La21 | CR Senne/Dyle-Gette | 3 | 2026 | Jun | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
La21 | CR Senne/Dyle-Gette | 4 | 2026 | Jun | yes | plant removal | . | 2 people | manual | digging | 8 | plants | all plants | . | follow next year(s) | .
La22 | CR Senne/Dyle-Gette | 1 | 2021 | . | yes | plant removal |  | 1 people | manual | digging | 8 | plants |  |  | follow next year(s) | no
La22 | CR Senne/Dyle-Gette | 2 | 2024 | . | no | n/a |  | n/a | n/a | n/a | n/a | n/a |  |  | follow next year(s)
La22 | CR Senne/Dyle-Gette | 3 | 2026 | Jun | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
La23 | Riverine | 1 | 2026 | May | yes | plant removal | . | . | . | . | 100 | plants | all plants | Managed by riverine in 2026 after reception letter of DNF | . | .
La24 | CR Senne/Dyle-Gette | 1 | 2025 | summer | yes | plant removal |  | 2 people | manual | digging | 50 | plants | all plants |  | follow next year(s) | no
La24 | CR Senne/Dyle-Gette | 2 | 2026 | Apr | yes | kpi_check |  | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
La24 | CR Senne/Dyle-Gette | 3 | 2026 | Apr | yes | plant removal | . | 2 people | manual | digging | 36 | plants | all plants |  | follow next year(s)
La25 | Riverine | 1 | 2025 | summer | yes | plant removal |  | . | manual |  | 1 | plants | only plant parts (flower) |  | follow next year(s) | no
La25 | . | 2 | 2026 | Jun | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
La27 | CR Senne/Dyle-Gette | 1 | 2026 | Apr | yes | kpi_check |  | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
La27 | CR Senne/Dyle-Gette | 2 | 2026 | Apr | yes | plant removal | . | 1 people | manual | digging | 5 | plants | all plants |  | follow next year(s)
La28 | CR Senne/Dyle-Gette | 1 | 2026 | Aug | yes | plant removal | . | 2 people | manual | digging | 8 | plants | all plants | . | follow next year(s) | .
Pco1 | BE, Jardiniers Botaniques | 1 | 2025 | Jan | yes | plant removal |  | 2 people | manual |  | 2 | plants | all plants |  | follow next year(s) | before and after but no photos during the management
Pco1 | BE, Jardiniers Botaniques | 2 | 2025 | Dec | no | kpi_check | BE | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Pco2 | BE, Jardiniers Fleuristes | 1 | . | Nov | yes | plant removal | Jardiniers Fleuristes | 4 people | manual |  | 4 | m3
Pco2 | BE, Jardiniers Fleuristes | 2 | 2026 | Jul | yes | kpi_check | BE | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Lp1 | CR Senne/Dyle-Gette | 1 | 2023 | Jun | yes | plant removal | fieldworkers RIPARIAS | 4 people | manual |  | 1 | m3 | all plants |  |  | yes
Lp1 | CR Senne/Dyle-Gette | 2 | 2023 | Jul | yes | plant removal | CRDG | 2 people | manual |  | 0.1 | m3 | all plants
Lp1 | CR Senne/Dyle-Gette | 3 | 2023 | Sep | yes | plant removal | CRDG | 1 people | manual |  | 0.02 | m3 |  |  | follow next year(s)
Lp1 | CR Senne/Dyle-Gette | 4 | 2024 | Aug | yes | plant removal | CRDG | 2 people | manual |  | 0.005 | m3 | incomplete (few plants remaining) |  | follow next year(s)
Lp1 | CR Senne/Dyle-Gette | 5 | 2025 | summer | yes | plant removal | CRDG | 2 people | manual |  | 0.06 | m3 | all plants | Germination. | follow next year(s)
Lp1 | CR Senne/Dyle-Gette | 6 | 2026 | Aug | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
Lp1 | CR Senne/Dyle-Gette | 7 | 2026 | Aug | yes | plant removal | CRDG | 4 people | manual |  | 7 | plants | all plants | Mixed with helophytes | follow next year(s)
Lp2 | CR Senne/Dyle-Gette | 1 | 2023 | Aug-Sep | yes | plant removal |  | 4 people | manual |  | 90 | L | all plants |  | follow next year(s) | no
Lp2 | CR Senne/Dyle-Gette | 2 | 2024 | . | no | n/a |  | 6 people | n/a | n/a | n/a | n/a |  | No plants observed because of high level of water. | follow next year(s)
Lp2 | CR Senne/Dyle-Gette | 3 | 2025 | July | no | n/a |  | 3 people | n/a | n/a | n/a | n/a |  |  | follow next year(s)
Lp3 | CR Senne/Dyle-Gette | 1 | 2025 | May | yes | plant removal |  | 2 people | manual |  | 0.2 | m3 | all plants |  | follow next year(s) | no
Lp3 | CR Senne/Dyle-Gette | 2 | 2026 | Aug | yes | kpi_check | . |  | n/a | n/a | 1 | plant | . | . | follow next year(s) | no
Lp4 | CR Senne/Dyle-Gette | 1 | 2025 | summer | yes | plant removal |  | 1 people | manual |  | 25 | L | all plants |  | follow next year(s) | no
Lp4 | CR Senne/Dyle-Gette | 2 | 2026 | Aug | no | kpi_check | . | 1 people | n/a | n/a | n/a | plant | . | no more plants | follow next year(s) | no
Ch1 | Brabant wallon | 1 | 2021 | Jul | yes | plant removal | Province du Brabant wallon | 2 people | manual |  | 15 | m² | all plants | 15m² in a larger pond |  | yes
Ch1 | Brabant wallon | 2 | 2024 | . | yes |  |  | . | [5 empty] | Lot of plants remaining.
Ch1 | Brabant wallon | 3 | 2026 | Jul | yes | n/a | [7 empty] | no more actions | none
Ch2 | Riverine | 1 | 2021 | Jul | yes | plant removal | pond owner | 1 people | manual |  | 10 | m² | incomplete (plants remaining) | 15 m² garden pond
Ch2 | Riverine | 2 | 2021 | fall | yes | plant removal | . | . | . |  | . | . | all plants | .
Ch2 | Riverine | 3 | 2022 | . | yes | plant removal | . | . | . |  | . | . | all plants | .
Ch2 | Riverine | 4 | 2023 | . | yes | plant removal | . | . | . |  | . | . | all plants | .
Ch2 | Riverine | 5 | (>2024) | . | yes | plant removal | . | . | . |  | . | . | all plants | .
Ch2 | Riverine | 6 | 2026 |  | yes | plant removal | [6 empty] | all plants visible
Ch3 | UCL | 1 | 2023 | summer |  |  | UCL | 3 people | manual |  |  |  | all plants | After contact with CRDG.
Ch3 | CR Senne/Dyle-Gette | 2 | 2025 | summer | yes | plant removal |  | 4 people | manual |  | 5 | m3 | all plants | Dredging of the pond after Ch's manual extraction. | follow next year(s)
Ch3 | . | 3 | 2026 | Jun | yes | kpi_check | . | . | . | . | . | . | . | . | . | .
Ch4 | Riverine | 1 | 2022 | Aug | yes | plant removal |  | 1 people | ecosystem_switch |  | 40 | m² | complete (pond disparition) | Pond has been turned into swimming pool. | none
Ch4 | . | 2 | 2026 | . | no | kpi_check | . | . | . | . | . | . | . | . | . | .
Ch5 | CR Senne/Dyle-Gette | 1 | 2024 | May-Aug | yes | plant removal | fieldworkers RIPARIAS | 4 people | manual |  | 3 | m3 | all plants |  | . | yes
Ch5 | CR Senne/Dyle-Gette | 2 | 2025 | summer | yes | plant removal |  | 2 people | manual |  | 0.055 | m3 | incomplete (plants remaining) |  | . | .
Ch5 | CR Senne/Dyle-Gette | 3 | 2025 | fall | yes | plant removal |  | . | . |  | . | . |  | (planned; has this proceeded?) | dd26-08: Bram was informed that management is stopped | .
Ch5 | CR Senne/Dyle-Gette | 4 | 2026 | May | yes | kpi_check |  |  | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
Ch6 | CR Senne/Dyle-Gette | 1 | 2025 | summer | yes | plant removal |  | 7 people | manual |  | 1.6 | m3 | all plants |  | follow next year(s) | yes
Ch6 | CR Senne/Dyle-Gette | 2 | 2026 | Jun | yes | kpi_check |  |  | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s)
Ch6 | CR Senne/Dyle-Gette | 3 | 2026 | Jun | yes | plant removal |  | 1 people | manual |  | 0.01 | m3 | all plants |  | follow next year(s) | no
Ch7 | CR Senne/Dyle-Gette | 1 | 2025 | summer | yes | plant removal |  | 2 people | manual |  | 0.2 | m3 | all plants |  | follow next year(s) | no
Ch7 | CR Senne/Dyle-Gette | 2 | 2026 | Summer | yes | kpi_check |  |  | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s)
Ch7 | CR Senne/Dyle-Gette | 3 | 2026 | Summer | yes | plant removal |  | 2 people | manual |  | 0.002 | m3 | all plants |  | follow next year(s) | no
Lm1 | CR Senne/Dyle-Gette | 1 | 2024 | May-Aug | yes | plant removal |  | 1 people | manual |  | 1 | m² | all plants |  | follow next year(s) | yes
Lm1 | CR Senne/Dyle-Gette | 2 | 2025 | Oct | no | n/a |  | 2 people | n/a | n/a | n/a | n/a |  |  | follow next year(s)
Lm1 | CR Senne/Dyle-Gette | 3 | 2026 | May | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
Ed1 | BE | 1 | 2021 | Sep | yes | plant removal | BE | 1 people | manual |  | 10 | plants | all plants |  | follow next year(s) | yes
Ed1 | BE | 2 | 2022 | Sep | no | n/a | BE | 1 people | n/a | n/a | n/a | n/a |  |  | none (eradication complete) | yes
Ed2 | CR Senne/Dyle-Gette | 1 | 2024 | summer | yes | plant removal | fieldworkers RIPARIAS | 5 people | manual |  | 8 | m3 | all plants |  |  | yes
Ed2 | CR Senne/Dyle-Gette | 2 | 2025 | summer | yes | plant removal |  | 2 people | manual |  | 0.42 | m3 | incomplete (plants remaining)
Ed2 | Riverine | 3 | 2025 | summer | . | . | . | . | dredging |  |  |  | all plants |  | follow next year(s)
Ed2 | CR Senne/Dyle-Gette | 4 | 2026 | May | no | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
Ed3 | CR Senne/Dyle-Gette | 1 | 2025 | summer | yes | plant removal |  | 31 people | manual |  | 40.163 | m3 | all plants |  | follow next year(s) | yes
Ed3 | CR Senne/Dyle-Gette | 2 | 2026 | Aug | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | none | .
Ed3 | CR Senne/Dyle-Gette | 3 | 2026 | Aug | yes | plant removal |  | 1 people | manual |  |  |  | all plants |  | follow next year(s)
Ed4 | CR Senne/Dyle-Gette | 1 | 2025 | summer | yes | plant removal |  | 2 people | manual |  | 0.03 | m3 | all plants |  | follow next year(s) | no
Ed4 | CR Senne/Dyle-Gette | 2 | 2026 | Summer | yes | kpi_check |  |  | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
Ed4 | CR Senne/Dyle-Gette | 3 | 2026 | Summer | yes | plant removal |  | 2 people | manual |  | 1 | m3 | all plants | mixed with ceratophyllum | follow next year(s) | no
Eg1 | VMM | 1 | 2024 | Jun |  |  | VMM | 1 people | manual |  |  |  | all plants |  |  | https://drive.google.com/drive/folders/1R21VXaUQ-MHDKsZ6x6eDnYr2pP5iQAOE?usp=drive_link
Eg1 | VMM | 2 | 2025 | Jun |  |  | VMM | 1 people | manual |  |  |  | all plants | 1 - Occasioneel (<5%) | follow next year(s)
Eg1 | INBO | 3 | 2026 | Apr | no | kpi_check | INBO | . | n/a | n/a | n/a | n/a | n/a | presumably too early, revisit scheduled | . | .
Eg1 | INBO | 4 | 2026 | Jul | no | kpi_check | INBO | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Eg2 | VMM/Vlaamse Waterweg | 1 | 2024 | Jul | yes | plant removal | VMM | 4 people | manual |  | 700 | m² | all plants |  |  | https://drive.google.com/drive/folders/1T8Sadfy0J7B5fHGKfaaq1c5n8N2RBDNa?usp=drive_link
Eg2 | VMM/Vlaamse Waterweg | 2 | 2025 | Jun |  |  | VMM | 1 people | manual |  |  |  | all plants | 1 - Occasioneel (<5%) | follow next year(s)
Eg2 | INBO | 3 | 2026 | Apr | no | kpi_check | INBO | . | n/a | n/a | n/a | n/a | n/a | presumably too early, revisit scheduled | . | .
Eg2 | INBO | 4 | 2026 | Jul | yes | kpi_check | INBO | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Eg3 | ANB | 1 | 2023 |  | no | n/a | ANB | 1 people | n/a | n/a | n/a | n/a |  |  | follow next year(s) | no
Eg3 | ANB | 2 | 2026 | Jul | no | kpi_check | INBO | . | n/a | n/a | n/a | n/a | n/a | "op de locatie aangeduid door ANB is niets te vinden" (visit report; but was found near to location) | . | .
Eg3 | INBO | 3 | 2026 | summer | yes | kpi_check | INBO | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Eg4 | CRDG | 1 | 2024 | summer | yes | plant removal | CRDG | 1 people | manual |  | 2 |  | all plants |  | follow next year(s)
Eg4 | CRDG | 2 | 2025 | summer | no | n/a |  | 1 people | n/a | n/a | n/a | n/a |  |  | follow next year(s)
Eg5 | Riverine | 1 | 2025 | Jun | yes | plant removal | CRDG | 1 people | manual |  | 3 | plants |  |  |  | no
Eg5 | CR Senne/Dyle-Gette | 2 | 2025 | Oct | no | n/a |  | n/a | n/a | n/a | n/a | n/a |  |  | follow next year(s)
Eg5 | CR Senne/Dyle-Gette | 3 | 2026 | May | yes | kpi_check | . | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s) | .
Eg5 | CR Senne/Dyle-Gette | 4 | 2026 | May | yes | plant removal | CRS | 1 people | manual | . | 9 | plants | all plants | . | follow next year(s) | .
Pj1 | VMM | 1 | 2025 | Jul | yes | plant removal | contractant | 2 people | mechanical | excavator(s) | 10 | m² | all plants | Excavator (rupskraan) removed 20cm of topsoil, in exchange of clean soil (4-5m³) which was then sown. | follow next year(s) | Pj1_Wezembeek-Oppem - Google Drive
Pj1 | VMM | 2 | 2025 | Aug | yes | plant removal | VMM | 1 people | manual | digging | 1 | bag | all plants |  | follow next year(s) | .
Pj1 | INBO | 3 | 2026 | Apr | yes | kpi_check | INBO | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Pj2 | CR Senne/Dyle-Gette | 1 | 2024 | Jun | yes | plant removal |  | 2 people | manual | digging | 1 | m3 | all plants |  | follow next year(s)
Pj2 | CR Senne/Dyle-Gette | 2 | 2025 | summer | no | n/a |  | 1 people | n/a | n/a | n/a | n/a |  |  | follow next year(s)
Pj2 | CR Senne/Dyle-Gette | 3 | 2026 | summer | no | kpi_check |  | . | n/a | n/a | n/a | n/a | n/a | n/a | follow next year(s)
Kp1 | BE | 1 | 2024 | Aug | yes | plant removal |  | 3 people | manual |  | 250 | m² | all plants |  | follow next year(s) | yes
Kp1 | BE | 2 | 2025 | Sep | yes | plant removal |  | 2 people | manual |  | 50 | m² | all plants |  | follow next year(s) | yes (Arnaud)
Kp1 | BE | 3 | 2026 | Jul | yes | kpi_check | BE | . | n/a | n/a | n/a | n/a | n/a | . | . | .
Kp2 | KU Leuven (ANB) | 1 | 2025 | Jun | yes | plant removal | KU Leuven | 1 people | manual |  | 1.5 | m² | all plants |  | follow next year(s)
Kp2 | INBO | 2 | 2026 | Jun | yes | kpi_check | INBO | . | n/a | n/a | n/a | n/a | n/a | . | . | .

## C2_pops_not-managed
RIPARIAS | population code |  | target species |  | site details | [5 empty] | partners |  | population details | [5 empty] | eradication status
Action | popcode | pc_old | group | species | latitude | longitude | site | municipality | region | RSU | organisation | ownership | habitat | waterbody_size_m² | infested_area_m² | pop_size_quantity | pop_size_unit | comments | assessment_date | visit_base | eradication_status | eradication_feasibility
C2 | Zl4 |  | plants | Zizania latifolia | 50°50'02,2"N | 4°25'45,2"E | Woluwe Park | Sint-Pieters-Woluwe | BRU | 44 | BE, ETH | BE | Pond | 52037 | 1570.9 | N/A | N/A | Management actions begin in November 2026; it is difficult to analyze the management results given the timeframe. | 2026-02-12 | 1 | follow_up | 3_maybe
C2 | Zl5 |  | plants | Zizania latifolia | 50°52'52,5"N | 4°19'01,4"E | Koning Boudewijnpark | Jette | BRU | ? | BE, ETH | BE | Pond | 5590 | 324 | N/A | N/A | Invaded at different places along the banks. Management actions will not start during the Riparias project. | 2026-02-12 | 1 | follow_up | 3_maybe
C2 | Zl5 |  | plants | Zizania latifolia |  |  | Parc Roi Baudouin | Jette | BRU | 47 | BE, ETH | BE | Pond | 4796 | 323.6 | N/A | N/A | Not yet managed - Management planned for 2026, Preparation in progres |  |  |  | 3_maybe
C2 | La19 |  | plants | Lysichiton americanus |  |  | Chemin de la Source | Rixensart | WAL | 6 | CR Senne/Dyle-Gette |  | Pondbank | N/A |  | 6 | plants | No contact with the owner yet |  |  |  | 4_yes

## C2_actions_crayfish
Popcode_old | organisation | date | Species | Observation | method of eradication | manpower (hour*person) | result | aftercare | comments | photos
C01 | . | 2019/2021 | Procambarus clarkii |  | Preliminary sampling and trapping | 125 | >5000 individuals caught between the 06/2019 and the 05/2021 |  | Removed crayfish trapped every two weeks in order to reduce their abundance and reduce the dispersion risk (we punctualy stop catching during lockdown)
C01 | . | 2021 | Procambarus clarkii |  | fencing the pond | 40 |  |  |  | yes
C01 | . | 25 and 27/05/2021 | Procambarus clarkii |  | Capture/Mark/recapture | 10 | Crayfish population estimation between 750 to 900 individuals
C01 | . | 27 may 2021 | Procambarus clarkii |  | Fish rescue | 70 | 25 Cyprinus carpio and a lot of Carassius carassius |  | By electrofishing. Really difficult to do due to the amount of mud
C01 | . | June to october 2021 | Procambarus clarkii |  | dredging the pond | ? | Partially done due to technical problems |  | The pipe between the two ponds was blocked. The pond owner had to find a private company to unclog it.The pond was empty during the winter 2021/2022. But the most downstream discharge pipe is actually clogged and the downstream pond is once again full of water.
C01 | . | August 2023 | Procambarus clarkii |  | Lime application, sludge settling, ponds' restoration and containment to prevent escaping | 160 | No crayfishes caugth in the baited traps placed after liming |  | To check management' success trapping will continue in 2024 | yes
C01 | . | October 2024 | Procambarus clarkii |  | Trapping and visual control |  | 3 runs : nothing |  | To be check once again in 2025 | no
C01 | . | 2025 | Procambarus clarkii |  | Trapping and visual control |  | 3 runs : nothing |  | eDNA collected, waiting for results
C01 | . | 2026 | Procambarus clarkii |  | eDNA |  | nothing detected |  | We can considered this action is successfull
C02 | BE | August 2023 | Procambarus clarkii | With baited crayfish traps | Trapping and population density estimation | 32 | Monitoring of the crayfish population (Absence/presence) + estimation |  | First detection of the crayfish in Sept 2022, immediate start with the preparations to eradicate the population in concurrence with the management of the pond. Important: The Woluwe river flows through the pond, creating an additional difficulty of containment. Trapping and population density estimation with catch-release method during aug-sep 2023, prior to the pond drawdown | yes
C02 | BE | Sept-Nov 2023 | Procambarus clarkii | With baited crayfish traps | Pond drawdown and containment of crayfish to prevent escaping | 72 | Start of the management action winter 2023-2024 |  | draining the pond with an external contractor | yes
C02 | BE | June-July 2024 | Procambarus clarkii | With baited crayfish traps | Trapping | 24 |  |  | Aftermanagement, monitoring | no
C02 | BE | Summer 2025 | Procambarus clarkii | With baited crayfish traps | Trapping | ~ 32 | Monitoring of the crayfish population (Absence/presence) + estimation |  |  | yes

## Actions on C3 species performed (hidden)
Plants (Widespread) (C3) (attachment for report on C3 actions 2023)
PW01 | 50.562825 | 4.135396 | CRS | April 2021 | Ecaussines | Wallonia | Ludwigia grandiflora | 2 m² | manual extraction | 1 | all plants removed | No check up in 2022 | Management by the owner | No
PW02 | 50.880351 | 4.310021 | BE | Sept 2021 | Ganshoren | BCR | Impatiens glandulifera | 40m2 (small patch, not evenly distributed) | Manual extraction | 1 person (BE) | All plants pulled and removed | Check up in 2022 | nearby small creek | yes
PW02 | 50.880351 | 4.310021 | BE | Sept 2022 | Ganshoren | BCR | Impatiens glandulifera | 1 flowering plant observed on site | Manual extraction | 1 person (BE) | Plant removed and detroyed | Check up in 2023 | nearby small creek | yes
PW03 | 50.881421 | 4.393107 | BE | Sept 2021 | Evere | BRC | Ludwigia grandiflora | 2-3 small plants on the site (emerging population) | Manual extraction | 1 person (BE) | Plant removed and destroyed | Check up in 2022 | In pond in humid area (marsh) | yes
PW03 | 50.881422 | 4.393108 | BE | Sept 2022 | Evere | BRC | Ludwigia grandiflora | No plants detected | visual inspection on-site | 1 person (BE) | Plant eradicated | done, no more plants | In pond in humid area (marsh) | yes
PW04 | 50.602157 | 4.312875 | CRS | Sept 2021 | Nivelles | Wallonia | Hydrocotyle ranunculoides | 8 m² | manual extraction | 1 | all plants removed | No check up in 2022 | Management by the owner | yes (only of population before management)
PW05 | 50.606395 | 4.151170 | CRS | Sept 2021 | Braine-Le-Comte | Wallonia | Ludwigia grandiflora | 250 m² invaded before the dredging | dredging done by the province (no information received on this action) | personnel of the HIT | No information | No information | Management by the HIT | No
PW05 | 50.606395 | 4.151170 | CRS | June 2022 | Braine-Le-Comte | Wallonia | Ludwigia grandiflora | area before the manual extraction = 25 m² + 100 m² (clearly underestimated area after mapping) | manual extraction only on a small part of the site | 8 | Only a small part of the plants were removed / too difficult to remove the roots | Only the small spot seems to be eradicated but there is a new one on an another place. The management on the big spot didn't give any result. A mapping done end of october 2022 --> estimation of the invaded area = ± 3.000 m² | Management by the municipality and CRS | yes
PW06 | 163738 | 146200 | CRDG | May-October 2022 | Court-St-Etienne | Wallonia | Ludwigia grandiflora | pond totally covered (250m²) | Mechanical extraction and manual aftercare | 5 | all plants removed | Manual extractions in the period of August until October |  | yes
PW07 | 50.624307 | 4.089338 | CRS | June 2022 | Petit-Roeulx-Lez-Braine | Wallonia | Hydrocotyle ranunculoides | 30 m² | manual extraction | 1 | all plants removed | Check up in Oct 2022 some new plants removed | Management by the owner | yes (only of population before management)
PW07 | 50.624307 | 4.089338 | CRS | October 2022 | Petit-Roeulx-Lez-Braine | Wallonia | Hydrocotyle ranunculoides | some new plants removed | manual extraction | 1 | all plants removed | Check up in 2023 | Management by the owner | Yes (only remaining plants)
PW08 | 50.624307 | 4.089338 | CRS | June 2022 | Petit-Roeulx-Lez-Braine | Wallonia | Ludwigia grandiflora | 1 m² | manual extraction | 1 | all plants removed | Check up in Oct 2022 some new plants removed | Management by the owner | yes (only of population before management)
PW08 | 50.624307 | 4.089338 | CRS | October 2022 | Petit-Roeulx-Lez-Braine | Wallonia | Ludwigia grandiflora | some new plants removed | manual extraction | 1 | all plants removed | Check up in 2023 | Management by the owner | No
PW09 | 50.9335 | 4.6752 | VMM | 2022-06-22 | Leuven | Flanders | Ludwigia grandiflora |  | manual extraction | 1 | all plants removed | To check | Managed by team rat catchers (standard operation) | No
PW10 | 50.9386 | 4.6674 | VMM | 2022-06-22 | Haacht | Flanders | Ludwigia grandiflora |  | manual extraction | 1 | all plants removed | To check | Managed by team rat catchers (standard operation) | No
PW11 | 159068 | 153322 | Riverine | July 2022 | Lasne | Wallonia | Ludwigia grandiflora | small in 2 ponds | manual extraction | 1 | all plants removed | Check up in 2023 | after contact with CRDG
PW12 | 50.986192 | 4.503136 | ANB - Sport Vlaanderen | August 2022 | Zemst | VL-Br | Ludwigia grandiflora | small population on pond bank | manual extraction | 2 | all plants removed, full removal of root system cannot be guaranteed | check up to be done |  | yes (only of population before management)
PW13 | 50.9996 | 4.5504 | VMM | 2022-09-12 | Boortmeerbeek | Flanders | Ludwigia grandiflora |  | manual extraction | 1 | all plants removed | To check | Managed by team rat catchers (standard operation) | No
PW14 | 50.554691 | 4.283895 | CRS | October 2022 | Seneffe | Wallonia | Hydrocotyle ranunculoides | 25 m² | manual extraction | 6 | all plants removed | To check | Management by CR Senne + DNF | Yes
PW15 |  |  | BE | 2022-09-01 | BRC | Anderlecht | Heracleum mantegazzianum | 10 m2 | Manual extraction | 2 people (BE) | All plants removed